## Sheet1
Sprint | Feature | Initial Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
1 | Customer login | 5 | Week 1: 4; Week 2: 1
1 | Creating a home/landing page | 8 | Week 1: 2; Week 2: 6
1 | User registration | 13 | Week 1: 7; Week 2: 6
1 | Publisher Registration | 5 | Week 1: 1; Week 2: 4
2 | Create Books model in backend | 13 | Week 3: 9; Week 4: 4
2 | Create books model in frontend | 3 | Week 3: 1; Week 4: 2
2 | Create book search function | 5 | Week 3: 0; Week 4: 5
2 | Dockerisation of microservices | 3 | Week 3: 1; Week 4: 2
2 | CircleCI code build | 5 | Week 3: 2; Week 4: 3
2 | Setting up RDS instance | 3 | Week 3: 2; Week 4: 1
2 | Setting up unit tests | 8 | Week 3: 0; Week 4: 8
3 | Setting up PayPal API | 5
3 | Implementing order status | 5
3 | Implementing Book checkout | 13
3 | Deploying to EC2 | 5
3 | Customer Dashboard | 8
| Settting | Start | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
| Planned Hours | 107 | 17.8333 | 17.8333 | 17.8333 | 17.8333 | 17.8333 | 17.8333
| Actual Hours | 71 | 14 | 17 | 15 | 25
| Remaining Effort | 107 | 93 | 76 | 61 | 36 | 36 | 36
| Ideal Burndown | 107 | 89.1667 | 71.3333 | 53.5 | 35.6667 | 17.8333 | 0